## Project Planner
Team 7 Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 12 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) |  |  |  |  | % Complete (beyond plan)
Feature | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5
User Login/Signup/Delete Account | 12 | 1 | 21 | 2 | 100%
Use Case 01: Add To-Do List | 13 | 2 | 22 | 1 | 100%
Use Case 02: Render Markdown Notes | 14 | 3 | 22 | 8 | 100%
Use Case 03: Input a markdown file and output flashcards | 12 | 3 | 25 | 5 | 100%
Use Case 04: Change order of flash cards | 12 | 3 | 25 | 5 | 100%
Use Case 05: Find text in files | 17 | 1 | 25 | 2 | 100%
Use Case 06: Rename files | 17 | 1 | 25 | 2 | 100%
Use Case 07: Convert notes to pdf | 17 | 1 | 25 | 4 | 100%
Use Case 08: Visualize hours worked | 12 | 3 | 15 | 5 | 100%
Use Case 09: Track hours worked | 12 | 3 | 15 | 5 | 100%
Use Case 10: Add Tags to notes | 1 | 3 |  |  | 0%
Use Case 11: Add flashcards to mind map | 1 | 3 |  |  | 0%
Use Case 12: Share flashcards with other people | 1 | 3 |  |  | 0%
Use Case 13: Create pdf of flashcards to print | 1 | 3 |  |  | 0%
Use Case 14: Share notes | 1 | 3 |  |  | 0%
Use Case 15:Visualize time blocks | 1 | 3 |  |  | 0%